## Sheet1
Week of | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14
Due | 2019-07-29: Statement of Intent & Lit Review; 2019-08-05: Interim Talks; 2019-09-30: Final Report and Literature Review; 2019-10-07: Presentation Slides; 2019-10-14: Presentation
Week Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
[10 empty] | Statement of intent & Lit Review | Functional Motor demonstration unit | [5 empty] | Final Report Draft 1
| Finish Excel calculations | [8 empty] | Free Week - Movable | [8 empty] | Presentation Building | Presentation Practice
Final report draft 2
| Iteration 1 | [14 empty] | Website Building
| Test | Design | Design | Build | Build | Test | Test | Analysis
|  | Shop | [13 empty] | Motor - pump intergration
Intergrated with Pump
[9 empty] | Iteration 2 | [8 empty] | Motor - Pump characterisation
[9 empty] | Design | Design | Build | Test | Test | Analysis
Shop